## Cabin Task List
Cabin Task List
$ | Status | Description | Description (cont.) | Notes
FALSE | TRUE | Obtain municipal and state permits
FALSE | TRUE | Begin site work and excavation
FALSE | TRUE | Homesite scraped, leveled and pinned.
FALSE | TRUE | Erosion controls in place.
FALSE | TRUE | Underground plumbing in place.
FALSE | TRUE | Drain line inspection
FALSE | TRUE | Square building site 24'4" x 24'4"
FALSE | TRUE | Run extension cord from Tammy's house
FALSE | TRUE | Dump wheel barrels onto path from camper to cabin
FALSE | TRUE | Fill in camper trench
FALSE | TRUE | Install breaker box for camper site
FALSE | TRUE | Move delivery box
FALSE | TRUE | Run power to camper site
FALSE | TRUE | Install electrical conduit
FALSE | TRUE | Put gorilla tape on conduit inside of camper power pole
FALSE | TRUE | Rough-in electrical and plumbing under floors
FALSE | TRUE | Install wire in conduit
FALSE | TRUE | Fill in trench for power
FALSE | TRUE | Rake around building site to smooth dirt and route rain water properly
FALSE | TRUE | Clean and organize barn
FALSE | TRUE | Remove electric wire from fencing
FALSE | TRUE | Move gate from windy hill Dr. entrance to Tammy's barn
FALSE | TRUE | Use bobcat to move burn pile
FALSE | TRUE | Cut up dead tree
FALSE | TRUE | Fix hole in Angela's bathroom
FALSE | TRUE | Fix threshold into Angela's bathroom
FALSE | TRUE | Dig footers 18" wide x 4" deep
FALSE | TRUE | Dig out spot for shower
FALSE | TRUE | Slab form boards set.
FALSE | TRUE | Level building site
FALSE | TRUE | Type II and vapor barrier in place.
FALSE | TRUE | Rebar in place
FALSE | TRUE | Pre-slab pour inspection completed.
FALSE | TRUE | Slab poured.
FALSE | TRUE | Slab form boards pulled.
FALSE | TRUE | Mow Yard
FALSE | TRUE | Smooth dirt around cabin
FALSE | TRUE | Spread hay
FALSE | TRUE | Spread grass seed
FALSE | TRUE | Rake loose gravel into driveway
FALSE | TRUE | Seal RIGID box for leaks
FALSE | TRUE | Attach handle to Delivery box
FALSE | FALSE | Fix lawn mower
FALSE | FALSE | Spread gravel in driveway better
FALSE | FALSE | Pressure wash Tammy's house and clean with Miracle Mist
FALSE | FALSE | Pressure wash Tammy's propane tank and clean with miracle mist
FALSE | FALSE | Split firewood
FALSE | FALSE | Finish trail
FALSE | FALSE | Frame walls, roof and ceilings, including all door and window rough openings
TRUE | FALSE | Exterior wall sheathing installed.
TRUE | FALSE | Windows installed.
TRUE | FALSE | Roof sheathing completed.
FALSE | FALSE | Roof nailing completed.
FALSE | FALSE | Roof tiles or shingle material loaded
FALSE | FALSE | Install remaining subfloors
TRUE | FALSE | Apply exterior wall and roof sheathing
FALSE | FALSE | Rough-in remaining electrical and plumbing lines in wall, ceiling and floor cavities
FALSE | FALSE | Rough plumbing installed.
FALSE | FALSE | Rough HVAC (Heating, Ventilation, and Air-Conditioning) installed.
TRUE | FALSE | Rough electrical installed.
FALSE | FALSE | Rough frame inspections (municipal inspections: mechanical, plumbing, electrical and frame) completed.
FALSE | FALSE | Apply roof flashing and shingles
TRUE | FALSE | Install windows and exterior doors
FALSE | FALSE | Batts installed (wall insulation).
FALSE | FALSE | Drywall stacked or scheduled.
FALSE | FALSE | Pre-drywall Inspections
FALSE | FALSE | Drywall installed throughout the home.
FALSE | FALSE | Drywall nailing inspection completed.
FALSE | FALSE | Ceiling insulation installed (per plan). Note: not required between 1st and 2nd floors.
FALSE | FALSE | Drywall taped and textured in accordance with the approved home plan.
FALSE | FALSE | Exterior finishes will be started (brick, cementatious finish, stone or siding).
FALSE | FALSE | Apply exterior trim
FALSE | FALSE | Apply ceramic tile in baths
FALSE | FALSE | Finish plumbing and electrical work
FALSE | FALSE | Paint and wallpaper
FALSE | FALSE | Install finish flooring
FALSE | FALSE | Garage doors installed.
FALSE | FALSE | Interior door casings and doors installed.
FALSE | FALSE | All cabinets installed.
FALSE | FALSE | Base molding installation complete.
FALSE | FALSE | Ceiling molding and chair molding installed (if required per the approved plan).
FALSE | FALSE | Staircase railing and balusters installed (two story homes).
FALSE | FALSE | Finish electrical installed and operationally tested.
FALSE | FALSE | Finish plumbing installed and operationally tested.
FALSE | FALSE | Finish HVAC installed and operationally tested.
FALSE | FALSE | All flooring installed.
FALSE | FALSE | Appliances installed.
FALSE | FALSE | In some locations, flat work (sidewalks, patios and driveways) is formed, and the concrete is poured.
FALSE | FALSE | Interior painting applied.
FALSE | FALSE | All countertops installed.
FALSE | FALSE | Mirrors and shower enclosures installed.
FALSE | FALSE | Flat work (sidewalks, patios and driveways) is formed, and the concrete is poured.
FALSE | FALSE | Outside landscaping is started (weather permitting).
FALSE | FALSE | Install final hardware
FALSE | FALSE | Final Inspection
FALSE | FALSE | Touch-up for final inspection by homeowner
FALSE | FALSE | Owner final walk-through
FALSE | FALSE | Closing
FALSE | FALSE | Move in

## Cabin Shopping List
Cabin Shopping List
Status | Description | Product | Size | Qty | Cost | Total | Notes
FALSE | Wall sheathing | Huber R-9 Insulated panel | 2" 4' x 10' | 36 | 50 | 1800 | Lumus Building Supply in Oakwood should have availability
FALSE | Roof sheathing | Huber Zip | 5/8" 4' x 8' | 24 | 50 | 1200
FALSE | Wall Underlayment |  |  |  |  | 0
FALSE | Roof Underlayment | Tesla wrap |  |  |  | 0
FALSE | North Wall Windows |  | 36" x 54" | 2 | 175 | 350
FALSE | East Wall Windows |  | 36" x 72" | 2 | 250 | 500
FALSE | South Wall Windows |  | N/A | 0 |  | 0
FALSE | West Wall Windows |  | 36" x 54" | 2 | 175 | 350
FALSE | North Wall Door |  | 36" x 80" | 1 | 1200 | 1200
FALSE | South Wall Door |  | 36" x 80" | 1 | 600 | 600
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
TOTAL: | [5 empty] | 6000