## Sheet1
Home Timeline
Obtain municipal and state permits
Begin site work and excavation
Homesite scraped, leveled and pinned.
Erosion controls in place.
Slab form boards set.
Underground plumbing in place.
Type II and vapor barrier in place.
Pre-slab pour inspection completed.
Slab poured.
In some locations, flat work (sidewalks, patios and driveways) is formed, and the concrete is poured.
Slab form boards pulled.
Rough grade completed.
Frame floors
Rough-in electrical and plumbing under floors
Install first-floor subfloor
Frame walls, roof and ceilings, including all door and window rough openings
Exterior sheathing installed.
Windows installed.
Roof sheathing completed.
Roof nailing completed.
Roof tiles or shingle material loaded.
Install remaining subfloors
Apply exterior wall and roof sheathing
Rough-in remaining electrical and plumbing lines in wall, ceiling and floor cavities
Rough plumbing installed.
Rough HVAC (Heating, Ventilation, and Air-Conditioning) installed.
Rough electrical installed.
Rough frame inspections (municipal inspections: mechanical, plumbing, electrical and frame) completed.
Apply roof flashing and shingles
Install windows and exterior doors
Batts installed (wall insulation).
Drywall stacked or scheduled.
Pre-drywall Inspections
Drywall installed throughout the home.
Drywall nailing inspection completed.
Ceiling insulation installed (per plan). Note: not required between 1st and 2nd floors.
Drywall taped and textured in accordance with the approved home plan.
Exterior finishes will be started (brick, cementatious finish, stone or siding).
Apply exterior trim
Apply ceramic tile in baths
Finish plumbing and electrical work
Paint and wallpaper
Install finish flooring
Garage doors installed.
Interior door casings and doors installed.
All cabinets installed.
Base molding installation complete.
Ceiling molding and chair molding installed (if required per the approved plan).
Staircase railing and balusters installed (two story homes).
Finish electrical installed and operationally tested.
Finish plumbing installed and operationally tested.
Finish HVAC installed and operationally tested.
All flooring installed.
Appliances installed.
In some locations, flat work (sidewalks, patios and driveways) is formed, and the concrete is poured.
Interior painting applied.
All countertops installed.
Mirrors and shower enclosures installed.
Outside landscaping is started (weather permitting).
Install final hardware
Final Inspection
Touch-up for final inspection by homeowner
Owner final walk-through
Closing
Move in